## Data
Time | Location | President | Sales Manager | Sales Person | Customer | Project | Job Class | Job | Order | Material | Material Vendor | Installer | Est Order Status | Est Material Status | Est Install Status | Est UOM | Est Material Qty | Est Material Shipped | Est Material % Complete | Est Material Total Price | Est Material Invoiced | Est Material Payment | Est Install % Complete | Est Install Total Price | Est Install Invoiced | Est Install Payment | Est Commission | Est Total Revnue | Est Material Unit Cost | Est Material Total Cost | Est Material Unit Price | Est Material Margin % | Est Install Unit Cost | Est Install Total Cost | Est Install Unit Price | Est Install Margin % | Est Total Margin % | Est Total % Complete | Actual Order Status | Actual Material Status | Actual Install Status | Actual UOM | Actual Material Qty | Actual Material Shipped | Actual Material % Complete | Actual Material Total Price | Actual Material Invoiced | Actual Material Payment | Actual Install % Complete | Actual Install Total Price | Actual Install Invoiced | Actual Install Payment | Actual Commission | Actual Total Revnue | Actual Material Unit Cost | Actual Material Total Cost | Actual Material Unit Price | Actual Material Margin % | Actual Install Unit Cost | Actual Install Total Cost | Actual Install Unit Price | Actual Install Margin % | Actual Total Margin % | Actual Total % Complete
2018-01-01 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 | Item1 | Mat Vendor1 | Installer1 | Working | Quote | Quote | UOM1 | 100 | 0 | 0% | 1000 | 0 | 0 | 0% | 80 | 0 | 0 | 0 | 0 | 8 | 800 | 10 | 20% | 0.6 | 60 | 0.8 | 25% | 20.37% | 0% | Working | Quote | Quote | UOM1 | 100 | 0 | 0% | 1000 | 0 | 0 | 0% | 80 | 0 | 0 | 0 | 0 | 8 | 800 | 10 | 20% | 0.6 | 60 | 0.8 | 25% | 20.37% | 0%
2018-01-30 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 | Item1 | Mat Vendor1 | Installer1 | Submitted | Released not Ordered | Released not Ordered | UOM1 | 100 | 0 | 0% | 1000 | 0 | 0 | 0% | 80 | 0 | 0 | 0 | 0 | 8 | 800 | 10 | 20% | 0.6 | 60 | 0.8 | 25% | 20.37% | 0% | Submitted | Released not Ordered | Released not Ordered | UOM1 | 100 | 0 | 0% | 1000 | 0 | 0 | 0% | 80 | 0 | 0 | 0 | 0 | 8 | 800 | 10 | 20% | 0.6 | 60 | 0.8 | 25% | 20.37% | 0%
2018-02-28 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 | Item1 | Mat Vendor1 | Installer1 | Committed | Staged | Staged | UOM1 | 100 | 0 | 0% | 1000 | 0 | 0 | 0% | 80 | 0 | 0 | 0 | 0 | 8 | 800 | 10 | 20% | 0.6 | 60 | 0.8 | 25% | 20.37% | 0% | Committed | Staged | Staged | UOM1 | 100 | 0 | 0% | 1000 | 0 | 0 | 0% | 80 | 0 | 0 | 0 | 0 | 8 | 800 | 10 | 20% | 0.6 | 60 | 0.8 | 25% | 20.37% | 0%
2018-03-29 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 | Item1 | Mat Vendor1 | Installer1 | Committed | On Purchase Order | On Purchase Order | UOM1 | 100 | 0 | 0% | 1000 | 0 | 0 | 0% | 80 | 0 | 0 | 0 | 0 | 8 | 800 | 10 | 20% | 0.6 | 60 | 0.8 | 25% | 20.37% | 0% | Committed | On Purchase Order | On Purchase Order | UOM1 | 100 | 0 | 0% | 1000 | 0 | 0 | 0% | 80 | 0 | 0 | 0 | 0 | 8 | 800 | 10 | 20% | 0.6 | 60 | 0.8 | 25% | 20.37% | 0%
2018-04-27 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 | Item1 | Mat Vendor1 | Installer1 | Committed | Received | On Purchase Order | UOM1 | 100 | 0 | 0% | 1000 | 0 | 0 | 0% | 80 | 0 | 0 | 0 | 0 | 8 | 800 | 10 | 20% | 0.6 | 60 | 0.8 | 25% | 20.37% | 0% | Committed | Partially Received | On Purchase Order | UOM1 | 100 | 0 | 0% | 1000 | 0 | 0 | 0% | 80 | 0 | 0 | 0 | 0 | 8 | 800 | 10 | 20% | 0.6 | 60 | 0.8 | 25% | 20.37% | 0%
2018-05-26 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 | Item1 | Mat Vendor1 | Installer1 | Committed | Fully Shipped | On Purchase Order | UOM1 | 100 | 100 | 100% | 1000 | 1000 | 0 | 0% | 80 | 0 | 0 | 0 | 1000 | 8 | 800 | 10 | 20% | 0.6 | 60 | 0.8 | 25% | 20.37% | 50% | Committed | Fully Received | On Purchase Order | UOM1 | 100 | 0 | 0% | 1000 | 0 | 0 | 0% | 80 | 0 | 0 | 0 | 0 | 8 | 800 | 10 | 20% | 0.6 | 60 | 0.8 | 25% | 20.37% | 0%
2018-06-24 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 | Item1 | Mat Vendor1 | Installer1 | Committed | Invoiced | In Progress | UOM1 | 100 | 100 | 100% | 1000 | 1000 | 0 | 25% | 80 | 20 | 0 | 0 | 1020 | 8 | 800 | 10 | 20% | 0.6 | 60 | 0.8 | 25% | 20.37% | 62.5% | Committed | Partially Shipped | In Progress | UOM1 | 100 | 50 | 50% | 1000 | 500 | 0 | 10% | 80 | 8 | 0 | 0 | 508 | 8 | 800 | 10 | 20% | 0.6 | 60 | 0.8 | 25% | 20.37% | 30%
2018-07-23 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 | Item1 | Mat Vendor1 | Installer1 | Committed | Paid in Full | In Progress | UOM1 | 100 | 100 | 100% | 1000 | 1000 | 1000 | 50% | 80 | 40 | 0 | 0 | 1040 | 8 | 800 | 10 | 20% | 0.6 | 60 | 0.8 | 25% | 20.37% | 75% | Committed | Fully Shipped | In Progress | UOM1 | 100 | 100 | 100% | 900 | 900 | 0 | 25% | 80 | 20 | 0 | 0 | 920 | 8 | 800 | 9 | 11.11% | 0.6 | 60 | 0.8 | 25% | 12.24% | 62.5%
2018-08-21 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 | Item1 | Mat Vendor1 | Installer1 | Committed | Paid in Full | In Progress | UOM1 | 100 | 100 | 100% | 1000 | 1000 | 1000 | 100% | 80 | 80 | 0 | 0 | 1080 | 8 | 800 | 10 | 20% | 0.6 | 60 | 0.8 | 25% | 20.37% | 100% | Committed | Invoiced | In Progress | UOM1 | 100 | 100 | 100% | 900 | 900 | 0 | 75% | 85 | 63.75 | 0 | 0 | 963.75 | 8 | 800 | 9 | 11.11% | 0.7 | 70 | 0.85 | 17.65% | 11.68% | 87.5%
2018-09-19 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 | Item1 | Mat Vendor1 | Installer1 | Committed | Paid in Full | In Progress | UOM1 | 100 | 100 | 100% | 1000 | 1000 | 1000 | 100% | 80 | 80 | 0 | 0 | 1080 | 8 | 800 | 10 | 20% | 0.6 | 60 | 0.8 | 25% | 20.37% | 100% | Committed | Invoiced | Intsalled | UOM1 | 100 | 100 | 100% | 900 | 900 | 0 | 100% | 85 | 85 | 0 | 0 | 985 | 8 | 800 | 9 | 11.11% | 0.7 | 70 | 0.85 | 17.65% | 11.68% | 100%
2018-10-18 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 | Item1 | Mat Vendor1 | Installer1 | Closed | Paid in Full | In Progress | UOM1 | 100 | 100 | 100% | 1000 | 1000 | 1000 | 100% | 80 | 80 | 0 | 66 | 1014 | 8 | 800 | 10 | 20% | 0.6 | 60 | 0.8 | 25% | 20.37% | 100% | Committed | Partial Payment | Invoiced | UOM1 | 100 | 100 | 100% | 900 | 900 | 0 | 100% | 85 | 85 | 0 | 0 | 985 | 8 | 800 | 9 | 11.11% | 0.7 | 70 | 0.85 | 17.65% | 11.68% | 100%
2018-11-16 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 | Item1 | Mat Vendor1 | Installer1 | Closed | Paid in Full | Paid in Full | UOM1 | 100 | 100 | 100% | 1000 | 1000 | 1000 | 100% | 80 | 80 | 80 | 66 | 1014 | 8 | 800 | 10 | 20% | 0.6 | 60 | 0.8 | 25% | 20.37% | 100% | Closed | Paid in Full | Paid in Full | UOM1 | 100 | 100 | 100% | 900 | 900 | 900 | 100% | 85 | 85 | 85 | 34.5 | 950.5 | 8 | 800 | 9 | 11.11% | 0.7 | 70 | 0.85 | 17.65% | 11.68% | 100%
2018-01-15 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 change1 | Item1 | Mat Vendor1 | Installer1 | Working | Quote | Quote | UOM1 | 25 | 0 | 0% | 250 | 0 | 0 | 0% | 20 | 0 | 0 | 0 | 0 | 8 | 200 | 10 | 20% | 0.6 | 15 | 0.8 | 25% | 20.37% | 0% | Working | Quote | Quote | UOM1 | 25 | 0 | 0% | 250 | 0 | 0 | 0% | 20 | 0 | 0 | 0 | 0 | 8 | 200 | 10 | 20% | 0.6 | 15 | 0.8 | 25% | 20.37% | 0%
2018-02-13 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 change1 | Item1 | Mat Vendor1 | Installer1 | Submitted | Released not Ordered | Released not Ordered | UOM1 | 25 | 0 | 0% | 250 | 0 | 0 | 0% | 20 | 0 | 0 | 0 | 0 | 8 | 200 | 10 | 20% | 0.6 | 15 | 0.8 | 25% | 20.37% | 0% | Submitted | Released not Ordered | Released not Ordered | UOM1 | 25 | 0 | 0% | 250 | 0 | 0 | 0% | 20 | 0 | 0 | 0 | 0 | 8 | 200 | 10 | 20% | 0.6 | 15 | 0.8 | 25% | 20.37% | 0%
2018-03-14 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 change1 | Item1 | Mat Vendor1 | Installer1 | Committed | Staged | Staged | UOM1 | 25 | 0 | 0% | 250 | 0 | 0 | 0% | 20 | 0 | 0 | 0 | 0 | 8 | 200 | 10 | 20% | 0.6 | 15 | 0.8 | 25% | 20.37% | 0% | Committed | Staged | Staged | UOM1 | 25 | 0 | 0% | 250 | 0 | 0 | 0% | 20 | 0 | 0 | 0 | 0 | 8 | 200 | 10 | 20% | 0.6 | 15 | 0.8 | 25% | 20.37% | 0%
2018-04-12 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 change1 | Item1 | Mat Vendor1 | Installer1 | Committed | On Purchase Order | On Purchase Order | UOM1 | 25 | 0 | 0% | 250 | 0 | 0 | 0% | 20 | 0 | 0 | 0 | 0 | 8 | 200 | 10 | 20% | 0.6 | 15 | 0.8 | 25% | 20.37% | 0% | Committed | On Purchase Order | On Purchase Order | UOM1 | 25 | 0 | 0% | 250 | 0 | 0 | 0% | 20 | 0 | 0 | 0 | 0 | 8 | 200 | 10 | 20% | 0.6 | 15 | 0.8 | 25% | 20.37% | 0%
2018-05-11 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 change1 | Item1 | Mat Vendor1 | Installer1 | Committed | Received | On Purchase Order | UOM1 | 25 | 0 | 0% | 250 | 0 | 0 | 0% | 20 | 0 | 0 | 0 | 0 | 8 | 200 | 10 | 20% | 0.6 | 15 | 0.8 | 25% | 20.37% | 0% | Committed | Partially Received | On Purchase Order | UOM1 | 25 | 0 | 0% | 250 | 0 | 0 | 0% | 20 | 0 | 0 | 0 | 0 | 8 | 200 | 10 | 20% | 0.6 | 15 | 0.8 | 25% | 20.37% | 0%
2018-06-09 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 change1 | Item1 | Mat Vendor1 | Installer1 | Committed | Fully Shipped | On Purchase Order | UOM1 | 25 | 25 | 100% | 250 | 250 | 0 | 0% | 20 | 0 | 0 | 0 | 250 | 8 | 200 | 10 | 20% | 0.6 | 15 | 0.8 | 25% | 20.37% | 50% | Committed | Fully Received | On Purchase Order | UOM1 | 25 | 0 | 0% | 250 | 0 | 0 | 0% | 20 | 0 | 0 | 0 | 0 | 8 | 200 | 10 | 20% | 0.6 | 15 | 0.8 | 25% | 20.37% | 0%
2018-07-08 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 change1 | Item1 | Mat Vendor1 | Installer1 | Committed | Invoiced | In Progress | UOM1 | 25 | 25 | 100% | 250 | 250 | 0 | 0% | 20 | 0 | 0 | 0 | 250 | 8 | 200 | 10 | 20% | 0.6 | 15 | 0.8 | 25% | 20.37% | 50% | Committed | Partially Shipped | In Progress | UOM1 | 25 | 0 | 0% | 250 | 0 | 0 | 10% | 20 | 2 | 0 | 0 | 2 | 8 | 200 | 10 | 20% | 0.6 | 15 | 0.8 | 25% | 20.37% | 5%
2018-08-06 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 change1 | Item1 | Mat Vendor1 | Installer1 | Committed | Paid in Full | In Progress | UOM1 | 25 | 25 | 100% | 250 | 250 | 250 | 25% | 20 | 5 | 0 | 0 | 255 | 8 | 200 | 10 | 20% | 0.6 | 15 | 0.8 | 25% | 20.37% | 62.5% | Committed | Fully Shipped | In Progress | UOM1 | 25 | 25 | 100% | 225 | 225 | 0 | 25% | 20 | 5 | 0 | 0 | 230 | 8 | 200 | 9 | 11.11% | 0.6 | 15 | 0.8 | 25% | 12.24% | 62.5%
2018-09-04 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 change1 | Item1 | Mat Vendor1 | Installer1 | Committed | Paid in Full | Intsalled | UOM1 | 25 | 25 | 100% | 250 | 250 | 250 | 50% | 20 | 10 | 0 | 0 | 260 | 8 | 200 | 10 | 20% | 0.6 | 15 | 0.8 | 25% | 20.37% | 75% | Committed | Invoiced | In Progress | UOM1 | 25 | 25 | 100% | 225 | 225 | 0 | 75% | 21.25 | 15.9375 | 0 | 0 | 240.9375 | 8 | 200 | 9 | 11.11% | 0.7 | 17.5 | 0.85 | 17.65% | 11.68% | 87.5%
2018-10-03 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 change1 | Item1 | Mat Vendor1 | Installer1 | Committed | Paid in Full | Paid in Full | UOM1 | 25 | 25 | 100% | 250 | 250 | 250 | 100% | 20 | 20 | 20 | 0 | 270 | 8 | 200 | 10 | 20% | 0.6 | 15 | 0.8 | 25% | 20.37% | 100% | Committed | Invoiced | Intsalled | UOM1 | 25 | 25 | 100% | 225 | 225 | 0 | 100% | 21.25 | 21.25 | 0 | 0 | 246.25 | 8 | 200 | 9 | 11.11% | 0.7 | 17.5 | 0.85 | 17.65% | 11.68% | 100%
2018-11-01 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 change1 | Item1 | Mat Vendor1 | Installer1 | Closed | Paid in Full | Paid in Full | UOM1 | 25 | 25 | 100% | 250 | 250 | 250 | 100% | 20 | 20 | 20 | 16.5 | 253.5 | 8 | 200 | 10 | 20% | 0.6 | 15 | 0.8 | 25% | 20.37% | 100% | Committed | Partial Payment | Invoiced | UOM1 | 25 | 25 | 100% | 225 | 225 | 0 | 100% | 21.25 | 21.25 | 0 | 0 | 246.25 | 8 | 200 | 9 | 11.11% | 0.7 | 17.5 | 0.85 | 17.65% | 11.68% | 100%
2018-11-30 | Location1 | President 1 | Sales Manager1 | Sales Person1 | Customer1 | Project1 | Healthcare | Job1 | Order1 change1 | Item1 | Mat Vendor1 | Installer1 | Closed | Paid in Full | Paid in Full | UOM1 | 25 | 25 | 100% | 250 | 250 | 250 | 100% | 20 | 20 | 20 | 16.5 | 253.5 | 8 | 200 | 10 | 20% | 0.6 | 15 | 0.8 | 25% | 20.37% | 100% | Closed | Paid in Full | Paid in Full | UOM1 | 25 | 25 | 100% | 225 | 225 | 225 | 100% | 21.25 | 21.25 | 21.25 | 8.625 | 237.625 | 8 | 200 | 9 | 11.11% | 0.7 | 17.5 | 0.85 | 17.65% | 11.68% | 100%
Formulas:
Time = [Time, row above]+29